## 30 Year Costs
Buildings | Gargunnock Community Centre | BSS2019090 | Date | 10.01.20
Main Building or Day Centre or Both | Building Component Description | Defect / Maintenance Issue | Repair / Maintenance/ Replacement Action | Investigation Action | Nature of Repair C = Cyclical R = Repair M = main component replacement P = preventative action | Urgency 1 Urgent 2 Essential 3 Desirable | Year 1-2 | Year 3-5 | Years 5 -10 | Years 11-15 | Years 15-20 | Years 20-25 | Years 25-30
EXTERNAL
Both | Roof slates & flashings | Overall poor condition of slates, fixings, flashings, underfelt etc. |  | Find out exact extent of prior repair works, and information on the underlying condition on those parts of the roof that have been exposed and investigated; use the information to planned phased roof overhaul. (Note 1) | n/a | 1 | 0
MB | Roof slates & flashings | Movement in slates and possibly roof timbers around north and east pitches. |  | Check timber frame connections and ensure that there are no structural issues or ongoing movement. | n/a | 1 | 0
MB | Roof slates & flashings | Water ingress in four areas through roofs - described in detail in report. | Provisional sum allowance for notional localised work as not possible to cost at this stage until investigated. | Investigate if ongoing or historic. If ongoing undertake localised repairs to flashings/slates. | R | 2 | 1500
Both | Roof slates & flashings | Slipped, split or damaged slates. Loose fixings, and damaged sections of flashing. | Provisional sum allowances for minor ongoing reactive patch repairs until fully overhauled. |  | R | 2 | 1500
MB | Roof slates & flashings | Overall poor condition of slates, fixings, flashings, underfelt etc. | Overhaul slate roofs; replace slates or redress, reuse and part replace, replace underfelt, and repair any rotted sarking etc. Flashings should be lifted and closely checked, and if corroded/ thinning/ holed / split / or too short in areas, then they should be replaced. (Note 1) |  | M | 3 |  | 24000 | 24000
DC | Roof slates & flashings | Overall poor condition of slates, fixings, flashings, underfelt etc. To main hall roof only. | Overhaul slate roofs; replace slates or redress, reuse and part replace, replace underfelt, and repair any rotted sarking etc. Flashings should be lifted and closely checked, and if corroded/ thinning/ holed / split / or too short in areas, then they should be replaced. (Note 1) |  | M | 3 |  |  |  | 11500
Both | RWG's | Blocked downpipes, gutters, and ground level surface water gullies etc. Dipping gutters. Leaking joints. Cracked gully at DC. | Clear all gutters, downpipes and gullies. Fit gratings to downpipe outlets and improve gully connections. Refix dipping gutters to run to fall, and repair any leaking joints. |  | R | 1 | 700
Both | RWG's | Corrosion to RWG's | Treat corrosion, including lining gutters and repainting all. |  | P | 2 | 1500
Both | RWG's | End of life replacement. | Note cost provided but if not badly corroded internally and overhauled at early stage and then properly maintained RWG's should last. |  | M | 3 | [5 empty] | 8000
MB | Chimneys | Pointing deteriorated and some spalling. Concrete haunching to pots is dated and cracked and pots and cope may need repairs on close inspection. | Co-ordinate with roof flashing and stonework repointing repairs. Dress or repair spalling stones, repair cracked stone, repoint, replace or repair haunching and check pots and ventilation of flues. (Note 2) Provisional sum allowed. |  | R | 2 |  | 2000
DC | Chimneys (ex) | Lack of flue ventilation. | Improve flue ventilation. |  | R | 1 | 300
Both | Timber Verges / Eaves / soffits | External timbers to soffits, eaves, verges, dormers, and fascia's etc. are weathered and paintwork is worn. Corner box details are rotted in parts. | Replace or repair rotted timbers, improve eaves/ verge /over door corner box details. Provisional sum for rotted sections. |  | R & P | 2 | 2000
Both | Timber Verges / Eaves / soffits | External timbers to soffits, eaves, verges, dormers, and fascia's etc. | Redecorate. |  | C | 2 | 1650 |  | 1650 | 1650 | 1650 | 1650 | 1650
MB | Roof lights | Original cast iron roof light. | Overhaul/ remove, or replace when reroofing. |  | M | 2 | incl' in reroofing
MB | Roof void |  |  | Arrange for specialist rot, vermin, and insect investigation of roof timbers. Use the information to coordinate any internal rot repairs with external roof works. Treat any woodworm short term. (Note 4) | n/a | 1
MB | Extensions roofs | Surface algae and leaves on roof. No outlet gratings. | Clean surfaces, fit gratings to downpipe outlets. |  | R | 1 | 300
MB | Extensions roofs | There is a weak spot at the junction of the original and new south extension roof, due to the construction detail and the workmanship in this position. The top of the wall is exposed, slates loose, and the roof felt is deteriorated and water has entered the roof just above the gutter line. | Check roofs, and reform section at south extension. (Note 3) |  | R | 1 | incl'
Both | Extensions roofs | There is a weak spot at the junction of the original and extension roofs. |  | Investigate. (Note 4) | P | 2
Both | Extensions roofs | Flat roof covering reaching end of life. | Replace. |  | M | 3 | [5 empty] | 9500
MB | Extensions roof lights | No current defects and units are fairly new and should last. They may require some repairs in last years to seals etc.
Both | All roofs | General maintenance. | Periodic checks and clearing of gutters and flat roof surfaces , and moss etc. |  | C | 2 | 300 | 900 | 1500 | 1500 | 1500 | 1500 | 1500
MB | Walls - Stonework | Cracking was noted to south chimney gable wall where almost full height cracking extends up through pointing and stones. Pointing is open and stone damaged where this crack meets a low level overflow pipe penetration. | The cracks, and holes, should be repaired, and the gable monitored to ensure there is no further movement or opening up. The pipe should be removed and hole infilled if redundant, or if in use it may be better slightly extended beyond wall line. |  | R | 2 | 250
MB | Walls - Stonework | Fine cracking in areas. | Isolated repointing. |  | R | 2 | 500
MB | Walls - Stonework | Brown staining below overflow pipe at high level on south elevation at west end. | The pipe should be removed and hole infilled if redundant. Staining could be removed. |  | R | 3 | 150
MB | Walls - Stonework | Isolated small holes in stonework and some redundant metal fixings. | Minor infilling/pointing repairs required. If metalwork is left in stone and corroded it will damage the stone, so either remove or treat to deter corrosion. |  | R | 2 | 450
MB | Walls - Stonework | Localised cracked and holed stone at lower 1m on rear /west elevation. | Repair stone and cracks, and monitor for further movement. |  | R | 2 | 100
MB | Walls - Stonework | Pointing to most window openings is cracked and deteriorated in areas, cracked stone cill. | Repoint selective openings, and cill, as required. |  | R | 2 | 800
MB | Walls - Stonework | Some stonework slightly eroded and weathered, with very isolated surface spalling. One stone spalling badly at low elevation on front/east elevation. | Dress or repair isolated stones as required. Provisional sum. |  | R | 2 | 700
MB | Walls - Pointing | Stonework has been repointing in sections some time ago, and there is a more recent pointing repair around toilet vent pipe. Some pointing appears to be a harder cement based mix, and may cause the surrounding stone to deteriorate more rapidly. | General repointing required in the mid-term. It is very important to ensure repairs do not cause more stone damage. Ensure any repairs to stones and repointing etc. is undertaken by a suitably experienced person, and using the correct material specifications (e.g. softer lime mortar etc.Cost assumes some can be retained. |  | R | 2 |  |  |  | 4000
Both | Walls - Roughcast | Roughcast on MB older west extension, and on original walls of DC is dated, boss and cracked in areas. | Replace mid-term. |  | M | 2 |  |  | 6500
DC | Roughcast Lintols | Cracking to roughcast at window lintols. |  | Investigate to determine if structural crack through lintol or surface crack through roughcast only. If latter, then repoint. | n/a | 2
MB | Walls - Render to new extension | Cracking. | Form movement joints. |  | R | 2 | 600
MB | Walls - Timber cladding to new extension | Stain/paint finish to timber cladding and ply soffits. | Redecorate. |  | C | 2 | 0 | 300 | 300 | 300 | 300 | 300 | 300
Both | Walls - Timber cladding to Extensions | Paint finish to timber cladding. Hand overpainted. | Redecorate. (Note 5). |  | C | 2 |  |  | 1000 | 1000 | 1000 | 1000 | 1000
Both | Other - Ground levels | Ground level heights too high compared with floor levels, possible bridging of dpc and poor ventilation of underfloor voids. |  | Investigate to verify construction below floor and then determine action. Not possible to cost until investigated. | n/a | 1
Both | Other - Ground levels | Ground level heights too high compared with floor levels, possible bridging of dpc and poor ventilation of underfloor voids. | As a minimum allow for reducing ground level at front and reinstating vents. |  | R | 3 | 1500
MB extension | Windows and Sliding Door- Composite metal and timber units. | No current defects and units are fairly new and should last. They may require some repairs in last years to seals etc. |  |  | M
Both | Windows - Older UPVC | End of life. | Replace. |  | M | 2 |  |  | 12600
DC | Windows - Newer UPVC | End of life. | Replace. |  | M | 2 | [5 empty] | 4200
Both | Windows - Older UPVC | Defective sealant. | Partial replacement of sealant. |  | R | 3 | 850
MB | External doors - Timber | Older timber painted doors to front entrance and rear store. Slightly weathered and rotted timbers to base of doors, frames and threshold. | Repair and redecorate. |  | R | 2 | 300
MB | External doors - Timber | End of life. | Replace. |  | M | 2 |  |  |  | 1750
MB | External doors - Steel/ Part Glazed | Doors are new and in good condition. |  |  | M
Both | External lights | End of life. | Replace. |  | M | 2 |  |  |  |  | 1200
Both | Tarmac | The tarmacadam is surface eroded and pitting, and isolated cracks. There are localised potholes and breaking up mainly around entrance. | Localised pothole repairs in progress - costs excluded. |  | R |  | Excl'
Both | Tarmac | End of life. | Replace. |  | M | 3 | [6 empty] | 18000
Both | Concrete pavings | A few are cracked and unlevel. | Replace cracked ones and relay unlevel ones. |  | R | 3 | 500
Both | Concrete pavings | End of life. | Replace. |  | M | 3 |  |  |  |  | 3300
Both | Walls & fences - stone | Dated and some stones and pointing deteriorated. | Provisional allowance for minimal isolated repairs and patch repointing. |  | R | 3 |  |  |  | 750 |  |  | 750
Both | Walls & fences - Brick | Section of retaining wall at car park, which is part spalling etc. | Reform/repair /alter, and install proper sloping cope. (Alternatively could remove small wall and regrade ground.) |  | R | 2 | 1300
Both | Walls & fences - Brick | Section of retaining wall behind boiler house and rest of building. | Repoint when pointing starts to deteriorate. Its also likely the top course of bricks will need replaced or cope added. |  | R | 2 |  |  |  |  | 900
Both | Walls & fences - Timber | Preservative stain. | Replace. |  | C | 2 | 1000 |  | 2250 |  | 2250 |  | 2250
Both | Walls & fences - Timber | End of life. | Replace. |  | M | 2
INTERNAL
Both | Damp | Damp readings to various areas per main report. |  | Investigate as detailed in main report. Provisional sum for investigation, opening up suspect areas and improving three/four chimney flues ventilation as a minimum. No allowance for further work which may be required depending on investigation. | R | 1 | 2000
MB | Ground levels/floor heights. | Ground levels are high in relation to floor heights, and underfloor void ventilation may be inadequate. |  | Investigate as detailed in main report, opening up suspect areas below floors. Cannot make cost allowance for any rot repairs or for reducing ground levels or improving floor void ventilation until result of investigation known. Cost for investigation only incl' in above item. | n/a | 2
MB | Mould | Mould on walls at both entrance doors. This is likely down to condensation on cold solid walls, but may also be part due to saturation of external stonework /wall below projecting timber eaves. | Any external repairs should be undertaken first to ensure walls are not holding water and internally walls could be initially cleaned down regularly, and if mould does not disappear then internal relining may be the best thing, depending on other factors. Provisional sum. |  | R | 3 | 500
Both | Flooring - Lino | End of life. | Replace. |  | M | 3 | [6 empty] | 11000
MB | Flooring - Vinyl | End of life. | Replace. |  | M | 3 |  |  |  | 3500
MB | Flooring - Carpet | End of life. | Replace. |  | M | 3 |  |  | 1500
DC | Flooring - Resin | In theory resin surfaces should last indefinitely. |  |  | M
MB | Walls - Plaster | In the main hall above both movable partition openings, we noted fine vertical cracking around lintol ends. | It is likely just slight settlement at new opening and should be monitored, but no other action required unless it progresses |  | P |  | 0
MB | Walls - Plaster | Plaster is slightly damaged at low level in ground floor hallways and at doorway west store. | Isolated plaster repairs, and possibly add corner protectors. |  | R | 2 | 350
DC | Walls - Plaster (encompassing part timber linings to lower 1m or so of walls) | Plaster is intact but dated. | It may be necessary to reline the walls long term as plaster nears end of life, and if so consideration can be given to insulation upgrade. At current point, cost given for plasterboard relining without substantial upgrade. |  | M | 3 | [6 empty] | 5250
Both | Walls - Plasterboard linings | Plasterboard linings are fairly new and should last. |  |  | M
MB | Ceilings - Plaster | There is some cracking to original plaster ceiling in corridor / hall outside kitchen and damp staining to ceiling around internal cast iron downpipe in same area. | Isolated plaster repairs. Damp issue recorded separately under roofs. |  | R | 2 | 500
MB | Ceilings - Other linings | Damaged and inadequate lining to underside of stair. | Reline in fire resistant plasterboard. |  | R | 1 | 300
DC | Ceilings - Plaster | We could not examine closely. If hall ceiling is original plaster then it may need replaced long term as it nears end of life. | It may be necessary to reline the ceiling long term as plaster nears end of life, and if so consideration can be given to insulation upgrade. At current point, cost given for plasterboard relining without substantial upgrade. |  | M | 2 | [6 empty] | 4750
Both | Ceilings - Plasterboard | Plasterboard linings are fairly new and should last. |  |  | M
Both | Internal doors - Timber | The doors are mixed age. In theory even the older ones should be maintainable. See separate notes below on upgrading fire resistance and improving ironmongery. |  |  | M
MB | Internal doors - Timber | West store door is between a heated and unheated space and is uninsulated and poorly sealed at frame. | Replace door to improve insulative performance. |  | P | 1 | 850
MB | Internal doors - Timber part glazed FR doors. | Doors in fair condition, and should last if maintained.
MB | Movable partitions | Servicing | We understand there is an annual charge of around £1,000 for servicing the folding partitions. Client to verify actual cost. |  | P | 2 | 2000 | 3000 | 5000 | 5000 | 5000 |  | 5000
MB | Movable partitions | End of life. | Replace. |  | M | 3 | [5 empty] | 16000
Both | Decoration - internal common | Periodic redecoration | Periodic redecoration - costs assume emulsion of walls every 5 years and emulsion of ceilings and eggshell to timber linings etc. at greater intervals. |  | C | 3 | 4300 |  | 7000 | 4300 | 7000 | 4300 | 7000
Both | Sanitary fittings | End of life. | Replace. |  | M | 2 | [6 empty] | 11000
Both | Kitchen fittings incl' oven, hob and fridge, but excluding not fitted appliances | End of life. | Replace. |  | M | 2 |  |  |  | 7000
Both | Grouting & Sealant | End of life. | Replace. |  | C | 2 |  |  |  | 200 |  |  | 200
Both | Electrical Services - Lighting & Electrical wiring | End of life. | Replace. |  | M | 2 |  |  |  |  | 7500 | 7500
MB | Electrical Services - fire alarm & smoke detection & CO2 detector | End of life. | Part replace. |  | M | 2 |  |  |  | 5500
Both | Electrical Services - Ventilation | End of life. | Replace. |  | M | 2 |  |  |  | 8500
Both | Electrical Services - hand driers | End of life. | Replace. |  | M | 2 |  |  |  | 500
Both | Mechanical Services - Heat Source / Boiler-Distribution & radiators | Lack of heat distribution to radiators. |  | Arrange for heating engineer to investigate. Costs cannot be given until investigation undertaken. | n/a | 1
Both | Mechanical Services - Heat Source / Boiler-Distribution & radiators | End of life. | Replace. |  | M | 2 |  |  |  |  | 18000
Both | Water and drainage supplies | End of life. | Part replace. |  | M | 2 | [6 empty] | 3000
Both | Mechanical Services - Heat Source / Boiler-Distribution & radiators | Periodic inspections/ testing / servicing etc. (Note7) |  |  | C | 1 | 300 | 900 | 1250 | 1250 | 1250 | 1250 | 1250
Both | Electrical Services incl' Lighting and Emergency Lighting | Fixed wire testing |  |  | C | 1 |  | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Both | Lighting and Emergency Lighting | Periodic inspections/ testing / servicing etc. (Note7) |  |  | C | 1 | 300 | 450 | 750 | 750 | 750 | 750 | 750
Both | Electrical Services - Ventilation | Periodic inspections/ testing / servicing etc. (Note7) |  |  | C | 1 |  | 300 | 500 | 500 | 500 | 500 | 500
Both | Water and drainage supplies | Periodic inspections /Legionella inspections . (Note7) |  |  | n/a | 1 |  | 250 | 500 | 500 | 500 | 500 | 500
MB | Electrical Services - fire alarm & smoke detection & CO2 | Periodic inspections/ testing / servicing etc. (Note7) |  |  | n/a | 1 |  | 600 | 1000 | 1000 | 1000 | 1000 | 1000
Both | Asbestos register | Create resister or verify no ACM's present. | Cannot be costed as existing information unknown. Client to verify. |  | n/a | 1
Both | Energy measures | This is a complex issue - refer to main report. Any improvement works will depend on client choice. We recommend replacing the west store door as a minimum, but client may wish to take other measures in longer term such as upgrading wall and ceiling linings in DC hall, and west store. | MB - replacing the west store door - cost included under doors section above.
Both | Roof Insulation | Gaps in consistency and coverage of existing insulation in MB and check in DC roofs over kitchen and toilet. | Repair existing and improve roof insulation by addressing any gaps. |  | P | 3 | 1250
Both | Fire Issues/ Escape etc. | See main report section 4.2 | Provisional sum for improvements to emergency lighting and detection coverage. |  | n/a | 1 | 1000
Both | Fire Issues - External exit doors and disabled exit | See main report section 4.2 | Whilst no repairs are required, there have been comments made in the fire assessment that the door swings should open outwards in direction of escape. (Note 3. )Provisional sum for at least one door replacement and ironmongery improvements, plus lightweight /removable ramp. |  | n/a | 1 | 2000
| Fire Issues - Internal doors | See main report section 4.2 | Some minor repairs to improve fire seals. Also it may be necessary to replace the 'fire door' at foot of stairwell as existing one may no longer have sufficient fire resistance. Note fire engineer has not recommended upgrading this door or other doors from rooms to two storey building to create a 'protected zone' stairwell. Provisional sum for 3 door replacements, removing snib locks and ironmongery improvements. |  | R | 1 | 3500
| Fire Barriers / Cavity barriers | See main report section 4.2 | Checking and filling any fire path holes in roof voids separating different spaces. Provisional sum. |  | R | 1 | 500
| Sub totals | [5 empty] | 38400 | 34200 | 68800 | 62450 | 55100 | 59450 | 78150